## Sheet1
Task | Start Date | Days to complete
Preparing project proposal | 2014-11-14 | 3
Overview | 2014-11-17 | 1
Objectives | 2014-11-18 | 5
Target Users | 2014-11-18 | 5
Project Scope | 2014-11-18 | 5
Gantt chart | 2014-11-23 | 3
Primary Study | 2014-11-26 | 3
Problem Statement | 2014-11-26 | 3
System Features | 2014-11-29 | 2
Hardware/Software Requirements | 2014-12-01 | 1
Data flow diagram & Context Diagram | 2014-12-02 | 6
Entity relationship diagram | 2014-12-02 | 6
Data Dictionary | 2014-12-02 | 6
Prototype/System Interface Design | 2014-12-08 | 42
Compilation of Interim Report | 2014-12-20 | 7
Presentation and Demo | 2014-12-28 | 1
Meeting Minutes | 2014-12-29 | 1
41957